## Fundraising Figures - Prelude a
Prelude and Axanar Costs
Date | Film | Estimated Cost | Amount Raised | Comments
2014-03-01 | Prelude to Axanar | 10000 | 10000 | Original Kickstarter goal.
| Prelude to Axanar | 20000 | 20000 | Deferring payment to our VFX team and others
| Prelude to Axanar | 40000 | 40000 | We have doubled that to $ 40,000, allowing us to do everything better and more professionally.
| Prelude to Axanar | 57000 | 31171 | Extra money need for KS fees, rewards. “All those numbers are pretty accurate, but you never know what pops up.”
Stretch goals | Prelude Kickstarter | 10000 | 0 | Axanar corporate infrastructure
| Prelude Kickstarter | 10000 | 0 | Starfleet tunics, for Axanar
| Prelude Kickstarter | 10000 | 0 | Tobias Richter, for Axanar, not Prelude
Subtotals |  | 157000 | 101171 | Kickstarter page has PayPal link to direct donation after campaign ended.
|  |  | 10164 | KS 10% fees
| Additional Income |  | 22826 | BackerKit income from post-campaign fundraising?
Totals | Actual Cost | 133449 | 123997 | Carried forward to Annual Report
| Balance |  | -9452 | Deficit
Axanar Infrastructure Kickstarter
July-August 2015 | Set Construction/Infrastructure | 125000 | 100000 | Original Kickstarter goal.
| Soundstage | 155000 | 155000 | $650K is low-end estimate of Axanar on Kickstarter
| Soundstage Renovation | 62000 | 62000 | “The budget is in process based on learnings from the Prelude to Axanar budget, so I would expect the budget to climb [higher than $750K].”
2015-08-24 | Axanar Pre-production | 50000 | 50000 | "Due to all your generosity, we have everything we need for the sets and studio and are well on our way to covering most of the budget. So we are going to start working on a formal budgeting process for Axanar and get those numbers as soon as possible.”
| Axanar Production Costs | 425000 | 271471
Subtotals |  | 817000 | 638471 | This first Kickstarter will be for the sound stage and set construction. Anything over what we need for that will be applied to the feature production costs.
| Actual Spending | 641797 | 638471 | Net income from KS
|  |  | -3326 | Deficit
|  |  | -2452 | Carry-fwd deficit from Prelude
|  | 647575 | -5778 | Total Deficit
Axanar Indiegogo | Production Budget | 1320000 | 574434 | Greenlighted first two “episodes”
No spending data

## Prelude Costs Chart - Prelude C
Prelude Cost Chart
| Estimated Costs | Ascending Goals | Amounts Raised | Ascending $ Raised | Amount Raised | Funding Goals | Actual Spending
Original Goal | 10000 | 10000 | 10000 | 10000 | 10000 | 10000
VFX | 20000 | 30000 | 20000 | 30000 | 30000 | 30000
2x = Quality | 40000 | 70000 | 40000 | 70000 | 70000 | 70000
Fees, Rewards | 57000 | 127000 | 31171 | 101171 | 101171 | 127000
Corp. Costs | 10000 | 137000 | 0 | 101171 | 101171 | 137000
Axanar Tunics | 10000 | 147000 | 0 | 101171 | 101171 | 147000
Axanar VFX | 10000 | 157000 | 0 | 101171 | 101171 | 157000
Post-Campaign Income |  |  | 22826 | 123997 | 123997 | 157000 | 133449

## Axanar Kickstarter+Indiegogo
|  | Amount Raised |  | Funding Goals | Actual Spending
Original Goal, Set Construction | 100000 | 100000 | 125000 | 125000
Soundstage Rental | 155000 | 255000 | 155000 | 280000
Soundstage Renovation | 62000 | 317000 | 62000 | 342000
Axanar Pre-production | 50000 | 367000 | 50000 | 392000
Axanar Production Costs | 271471 | 638471 | 425000 | 817000
Indiegogo | 574434 | 1212905 | 1320000 | 1958471 | 647575
‘Axanar’ Budget Gap